ATWIMA MPONUA DISTRICT ASSEMBLY

(NYINAHIN)

2026 DISTRICT COMPOSITE ANNUAL ACTION PLAN AND BUDGET

PREPARED BY:

DISTRICT PLANNING CO-ORDINATING UNIT (DPCU)

SEPTEMBER,2025

| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme (PBB) | Sub Programme (PBB) | Broad Activities | Location | Time Frame |  |  |  | Funding Source |  |  |  | Programme Status |  |  | Implementing Institution/ Department |  |
|  |  |  |  | 1ST | 2ND | 3RD | 4TH | DACF GH₵ | IGF GH₵ | DACF-RFG GOG GH₵ | New |  | On-going | Lead |  | Colla- borating |
| PRIVATE SECTOR DEVELOPMENT (FINANCE DEPARTMENT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance and Revenue Mobilization | - Ceded Revenue Collection by Area Councils and Establish Revenue Task Force and assign roles for effective and efficient revenue collection | All 12 Area Councils |  |  |  |  |  | 36,000 (IGF) (3,000 each) |  |  |  |  | Cent. Admin |  | Finance |
| Management and Administration | Finance and Revenue Mobilization | - Organise sensitization on property rate generation | All 12 Area councils |  |  |  |  |  | 3,000 (IGF) |  |  |  |  | Cent. Admin |  | Finance |
| Management and Administration | Finance and Revenue Mobilization | - Train and build capacity of revenue collectors | Nyinahin |  |  |  |  | 10,000 | 5,000 |  |  |  |  | Cent. Admin |  | Finance |
| Management and Administration | Finance and Revenue Mobilization | - Procure value books | AMDA |  |  |  |  | 30,000.00 |  |  |  |  |  | Cent. Admin |  | Finance |
| Management and Administration | Finance and Revenue Mobilization | - Preparation of revenue improvement Action Plan | AMDA |  |  |  |  | 3,000 |  |  |  |  |  | Cent. Admin |  | Finance |
| Management and Administration | Finance and Revenue Mobilization | - Acquire and develop a database revenue software | AMDA |  |  |  |  | 50,000 |  |  |  |  |  | Cent. Admin |  | Finance, Budget and Revenue |
| PRIVATE SECTOR DEVELOPMENT (BUSINESS ADVISORY CENTRE) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, Tourism, and Industrial development | 6. Training youth women groups on additional livelihood | Nyinahin |  |  |  |  | 10,000 (DACF) |  |  |  |  |  | BAC |  | Cent. Admin. |
| Economic Development | Trade, Tourism, and Industrial development | - Facilitate women groups to acquire credit facilities | Nyinahin |  |  |  |  |  | 7,000 (IGF) |  |  |  |  | BAC |  | Cent. Admin. |
| Economic Development | Trade, Tourism, and Industrial development | - Clearing site and exhibition of of Amanano river | Kasutia |  |  |  |  | 10,000 (DACF) |  |  |  |  |  | BAC |  | Cent. Admin. |
| Economic Development | Trade, Tourism, and Industrial development | - Support to Local Economic Development (LED) through technical skills training in Products Packaging, branding, Labelling and cassava processing | Women and youth (Nyinahin) |  |  |  |  | 20,000 (DACF) |  |  |  |  |  | Trade & Industry BAC |  | Cent. Admin. |
| Economic Development | Trade, Tourism, and Industrial development | 10. Train young women in Soap and Detergent Making, Beads Making, Baking, etc. | Women groups |  |  |  |  | 20,000 (DACF) |  |  |  |  |  | Trade & Industry BAC |  | Cent. Admin. |
| Economic Development | Trade, Tourism, and Industrial development | - Dredging and exhibition of Amanano river tourist site | Nyinahin |  |  |  |  |  | 10,000 (IGF) |  |  |  |  | Cent. Admin. |  | Trade & Industry BAC |
| AGRICULTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance and Administration | Agricultural Development | - Fuel and maintain official vehicle | Different locations |  |  |  |  |  |  | 4000 GOG |  |  |  | Agric Dept. |  | BMA (RAD) |
| Finance and Administration | Agricultural Development | - Payment of utility bills ,purchase of equipment and stationaries. | Different locations |  |  |  |  |  |  | 4000 (GOG) |  |  |  | Agric Dept. |  | BMA (RAD) |
| Policy planning , budgeting and , monitoring and evaluation | Agricultural Development | - Conduct 72 supervisory and monitoring visits each by 6 DAOs by the end of December 2026 to monitor the activities of AEAs | Dist. wide |  |  |  |  |  |  | 4800 (GOG) |  |  |  | Agric Dept. |  | (M&E-RAD) |
| Policy planning , budgeting and , monitoring and evaluation | Agricultural Development | - Conduct 8 routine monitoring visit by DDA by the end of December , 2026 on post-harvest loses | Different locations |  |  |  |  |  | 3,000.00 (IGF) |  |  |  |  | Agric Dept. |  | (M&E-RAD) MPUC |
| Policy planning , budgeting and , monitoring and evaluation | Agricultural Development | - Organise of farmers day | Dist. wide |  |  |  |  | 70,000.00 (DACF) |  |  |  |  |  | Agric Dept. |  | ( DDA) |
| Production and productivity improvement | Agricultural Development | - Establish 2 (0.5 acre) demonstration of cereals and legume strip intercropping system In four communities in the district by the end of June 2026. | Nyinahin |  |  |  |  |  |  | 2000 (GOG) |  |  |  | Agric Dept. |  | Crops & Ext-RAD). |
| Production and productivity improvement | Agricultural Development | - Establish a demonstration on rabbit rearing to promote its production among women by the end of June 2026 | Different locations |  |  |  |  |  |  | 1700 (GOG) |  |  |  | Agric Dept |  | (APD- RAD) |
| Production and productivity improvement | Agricultural Development | - Conduct 8 field days for the 4cereal legume strip demonstration in the 4 operational areas by the end of September 2026. | Different locations |  |  |  |  |  | 600 (IGF) |  |  |  |  | Agric Dept |  | Crops & Ext-RAD). |
| Production and productivity improvement | Agricultural Development | - Carry out farm visit to each of the 6 AEAs by the end of December 2026 to provide extension service to value chain actors along the agric value chain . | 6 AEAS zones |  |  |  |  |  |  | 3600 (GOG) |  |  |  | Agric Dept |  | (Ext-RAD). |
| Production and productivity improvement | Agricultural Development | - Educate 100 female farmers in 4 zones on Village Savings and Loan Association (VSAL)scheme by the end of March 2026. | Different Locations |  |  |  |  |  | 600 (IGF) |  |  |  |  | Agric Dept |  | (WAD-RAD) GHS |
| Post- Harvest Management and Agricultural Marketing | Agricultural Development | - Link 200 maize ,rice and plantain farmers identified aggregators and processors along the agric value chain by end of December 2026. | District Wide |  |  |  |  |  |  | 600 (GOG) |  |  |  | Agric Dept |  | (SRID –RAD) |
| Post- Harvest Management and Agricultural Marketing | Agricultural Development | - Train 300 farmers on post –harvest management (drying , sorting , bagging ,etc.) for grains and vegetables to reduce losses and aflatoxins by end of December 2026. | District wide |  |  |  |  |  | 1000 (IGF) |  |  |  |  | Agric Dept |  | (Crops ,Engineer –RAD) |
| Early Warning System and Emergency Preparedness . | Agricultural Development | - Sensitize farmers (300) in 2 operational areas on disease surveillance and management of FAW (3rd quarter ) | Nyinanahin, and Adupri |  |  |  |  |  | 600 (IGF) |  |  |  |  | Agric Dept |  | PPRSD |
| Early Warning System and Emergency Preparedness | Agricultural Development | - Sensitize 18 Agro – input dealers and 16 staff in the District on safety precautions and proper ways of keeping or handling of agrochemical and basic principles in the usage of agrochemicals (3rd quarter ) |  |  |  |  |  |  |  | 700 (GOG) |  |  |  | Agric Dept |  | PPRSD |
| SOCIAL DEVELOPMENT (EDUCATION) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Education and Youth Development | - Procure and supply dual desk, mono desk, octagonal tables and chairs for K.G and teachers table and chairs to different locations in the district. | Dist. wide |  |  |  |  | 2,137,687.35 (DACF) |  |  |  |  |  | Works Dept. |  | Cent. Admin. GES |
| Social Service Delivery | Education and Youth Development | - Support to district education fund and monitoring activities of GES | Nhynahin |  |  |  |  | 50,029.28 (DACF) |  |  |  |  |  | Finance |  | Cent. Admin. GES |
| Social Service Delivery | Education and Youth Development | - Support to the participation of STEM activities in the district | Dist. wide |  |  |  |  | 20,000.00 (DACF) |  |  |  |  |  | GES |  | Cent. Admin. GES |
| Social Service Delivery | Education and Youth Development | - Support for the conduct of Mock Exam, BECE and WASSCE in the District. | Dist. wide |  |  |  |  | 50,000.00 (DACF) |  |  |  |  |  | GES |  | Cent. Admin. GES |
| Social Service Delivery | Education and Youth Development | - Support for the expansion of school feeding programme | Dist. wide |  |  |  |  | 80,000 (DACF) |  |  |  |  |  | GES |  | Cent. Admin. |
| Social Service Delivery | Education and Youth Development | - Organise my first day at school in the district | Dist. wide |  |  |  |  | 50,000.00 (DACF) |  |  |  |  |  | GES |  | Cent. Admin. |
| Social Service Delivery | Education and Youth Development | - Facilitate the organisation of sports activities in the district | Dist. wide |  |  |  |  | 50,000 (DACF) |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Social Service Delivery | Education and youth development | - Support for the Organization of Independence day Anniversary | Dist. wide |  |  |  |  | DACF 80,000.00 |  |  |  |  |  | GES |  | Cent. Admin |
| Social Service Delivery | Education and youth development | - Support for the Organization of DEOC meetings | Nyinahin |  |  |  |  | DACF 20,000.00 |  |  |  |  |  | GES |  | Cent. Admin |
| Social Service Delivery | Education and youth development | - Construction of 1No. 6unit classroom block, staff common room, office store, 4-unit W/C toilet facility with 1No. mechanized borehole | Agogoso DA |  |  |  |  | 548.000.00 (DACF) |  |  |  |  |  | GES |  | Cent. Amin |
| Social Service Delivery | Education and youth development | - Construction of 1No. 2-unit K.G. block with dressing room, office, store, 4-unit W/C toilet facility, furnishing and a mechanized borehole. | Kramokrom |  |  |  |  | 652,687.35 (DACF) |  |  |  |  |  | GES |  | Cent. Admin |
| SOCIAL DEVELOPMENT (DISTRICT HEALTH DIRECTORATE) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Health Delivery | - Support to district Response initiative on roll back Malaria, cholera, immunization and disease outbreak. | District wide |  |  |  |  | 68,843.67 DACF |  |  |  |  |  | Health Directorate |  | Cent. Admin. |
| Social service Delivery | Health Delivery | - Provision of Support to the Health Directorate | Nyinahin |  |  |  |  | 100,000.00 |  |  |  |  |  | Heath Directorate |  | Cent. Admin |
| Social service Delivery | Health Delivery | - Provision of support for HIV AIDS activities in the District | Nyinahin |  |  |  |  | 106,884.3674 |  |  |  |  |  | Health Directorate |  | Cent. Admin |
| Social Service Delivery | Health Delivery | - Construction of 2No. CHPS compound, furnishing and Drill 2No. mechanized borehole | Mpasatia, Wansamire |  |  |  |  | 2, 000,000 |  |  |  |  |  | Health Directorate |  | Cent. Admin. |
| Social Service Delivery | Health Delivery | - Facilitate disease surveillance in the district. | Dist. wide |  |  |  |  | 0,000.00 |  |  |  |  |  | Health Directorate |  | Cent. Admin |
| Social Service Delivery | Health Delivery | - Organise public health emergency responds initiative and meetings | Dist. wide |  |  |  |  | 68,843.67 |  |  |  |  |  | Health Directorate |  | Cent. Admin |
| SOCIAL PROTECTION ( SOCIAL WELFARE AND COMMUNITY DEVELOPMENT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Social Welfare and Community Development | - Sensitize 10 communities on Gender based and domestic violence | 10 communities |  |  |  |  | 7000 (DACF) |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Management of LEAP cases in the district | Dist. wide |  |  |  |  | 20,000 (DACF) |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Sensitize 30 communities on child labour, child abuse and other related issues in the district | Dist. wide |  |  |  |  | 10,000 (DACF) |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Sensitize 40 communities on causes and effects of teenage pregnancy in the district | 40 communities |  |  |  |  | 10,000 DACF |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Register and handle reported child protection cases in the district | Dist. wide |  |  |  |  | 4,000 DACF | 4,000 (IGF) |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Management of persons with Disability, registration of PWD fund | Dist. wide |  |  |  |  | 10,717.51 (DACF) |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Disbursement of Disability fund | Dist. wide |  |  |  |  | 7,550 (DACF) |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Sensitize girls and women in PWDs in 6 communities on the need to participate in community decision making | Selected communities |  |  |  |  | 4,000 (DACF) |  |  |  |  |  | DSW/ CD |  | Cent. Admin. |
| Social Service Delivery | Social Welfare and Community Development | - Sensitize DCPC and CCPC members on CLMRS | Nyinahin |  |  |  |  | 6,000.00 |  |  |  |  |  | DSW/CD/ NGOs |  | Cent. Admin |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DISTRICT ENVIRONMENTAL HEALTH UNIT (DEHU) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster prevention and Management | - Evacuation of Refuse dams and maintenance of final damping site | Different location |  |  |  |  | 630,000,00 (DACF) |  |  |  |  |  | DEHO |  | Cent. Admin |
| Environmental and Sanitation Management | Disaster prevention and Management | - Food Vendor Screening in the District | District wide |  |  |  |  |  | 4,000 (IGF) |  |  |  |  | DEHO |  | Cent. Admin |
| Education and youth development | Disaster prevention and Management | - Rehabilitation of Public toilet | Nyinahin |  |  |  |  | 200,000.00 |  |  |  |  |  | DEHO |  | Cent Admin |
| Environmental and Sanitation Management | Disaster prevention and Management | - Observe national sanitation Day.(Provision of sanitation improvement package and sanitation equipment drugs and disinfectant by the assembly) | Dist. Wide |  |  |  |  | 387,205 |  |  |  |  |  | DEHO |  | Cent. Admin |
| Environmental and Sanitation Management | Disaster prevention and Management | - Formation of sanitation Task force and National clean up exercise | Nyinahin |  |  |  |  | 30,000.00 |  |  |  |  |  | DEHO |  | Cent. Admin |
| Environmental and Sanitation Management | Disaster prevention and Management | - Control noise and air pollution | Dist. wide |  |  |  |  | 10,000.00 |  |  |  |  |  | DEHO |  | Cent. Admin |
| Environmental and Sanitation Management | Disaster prevention and Management | - Fumigation and disinfection of open spaces to control airborne diseases | Dist. wide |  |  |  |  | 366,275.00 |  |  |  |  |  | DEHO |  | Cent. Admin |
| INFRASTRUCTURE (WORKS DEPARTMENT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | - Completion of 1no. 2unit KG block, four water closet toilet facility, office and a mechanized borehole and store | Kotokuom |  |  |  |  |  |  | 118,234.00 DDF |  |  |  | Works Dept. |  | Cent. Admin. |
| Infrastructure Delivery and Management | Infrastructure Development | - Drill and Mechanised 10 no. Boreholes | Different locations |  |  |  |  | 2, 137,687.35 |  |  |  |  |  | Works Dept |  | Cent. Admin |
| Infrastructure Delivery and Management | Infrastructure Development | - Construction of a 24 Hour economy model market | Nyinahin |  |  |  |  | 5,344,218.37 |  |  |  |  |  | Works Dept |  | Central Admin |
| Infrastructure Delivery and Management | Infrastructure Development | - Drill and Mechanised 2No. borehole at | Tanodumaasi and Adupri |  |  |  |  |  |  | 89,438.64 |  |  |  | Works Dept. |  | Cent. Admin. |
| Infrastructure Delivery and Management | Infrastructure Development | - Procure and Deliver furniture | Different locations |  |  |  |  |  |  | 100,000 |  |  |  | Cent. Admin. |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Completion of paved lorry park with sheds and 10 seater W/C toilet | Nyinahin |  |  |  |  |  |  | 267,736 |  |  |  | Works Dept |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Completion of 1No.community centre | Nyinahin |  |  |  |  | 754,104.22 |  |  |  |  |  | Works Dept n |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | - Repair and maintenance of office equipment bungalows | Nyinahin |  |  |  |  | 512579 (DACF) |  |  |  |  |  | Cent. Admin. |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Completion of 1no. 8 unit holding centre at Nyinahin Hospital. | Nyinahin |  |  |  |  |  |  | 34,583.00 DAPT |  |  |  | Cent. Admin |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Construction of 20 seater W/C at Nyinahin D/A | Nyinahin |  |  |  |  |  |  | 245,823.00DPAT |  |  |  | Cent. Admin |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Construct and furnish of 2no. CHPS Compound | Mpasatia and Wamsanmire |  |  |  |  | 500,00 DACF |  |  |  |  |  | Cent. Admin |  | Works Dept |
| Infrastructure Delivery and Management | Infrastructure Development | - Construction of 1no. resident bungalow at collage of nursing and midwifery | Tano dumaasi |  |  |  |  |  |  | 495,052.50 DDF) |  |  |  | Cent. Admin |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Construction of 1No.6uint classroom block | Agogoso |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | - Construction of 1o.KG Block | Kramokrom |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | - Completion of 2No. 3unit primary schools | Ashiresu and Pakyi |  |  |  |  | DACF 1,108,208.45 |  |  |  |  |  | Cent. Admin |  | Works Dept. |
| Infrastructure Delivery and Management | Infrastructure Development | - Procure Hospital Equipment for 5No. CHPS Compound | Asamang, Okyerekrom, Wansanmire Kyerewere Donkoto |  |  |  |  | DACF 1,913,062.02 |  |  |  |  |  | Cent. Admin |  | Works Dept |
| SPATIAL PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | - Street Naming and Property Addressing Project. | Nyinahin |  |  |  |  | 30,000.00 (DACF) |  |  |  |  |  | PPD |  | Works Dept. Cent. Admin. |
| Infrastructure Delivery and Management | Physical and Spatial Planning | - Planning Scheme preparation and structural plans for the district under MTDP preparation | Mpasatia and Nyinahin |  |  |  |  | 50,000 (DACF) |  |  |  |  |  | PPD |  | Works Dept. Cent. Admin. |
| Infrastructure Delivery and Management | Physical and Spatial Planning | - Organise Technical joint site inspections on development control | Dist. wide |  |  |  |  | 10,000.00 | 22,000 (IGF) |  |  |  |  | PPD |  | Works Dept. Cent. Admin. |
| Infrastructure Delivery and Management | Physical and Spatial Planning | - Embark on Monthly Technical and Spatial Planning Committee Meetings | PTP |  |  |  |  |  | 56,000 (IGF) |  |  |  |  | PPD |  | Works Dept. Cent. Admin. |
| Infrastructure Delivery and Management | Physical and Spatial Planning | - Compensation to farmers (land owners) of the Agenda 111project | Nyinahin |  |  |  |  | 155,000 (DACF) |  |  |  |  |  |  |  | Works Dept. Cent. Admin |
| ROAD PROGRAMMES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure delivery and Management | Infrastructure Development | - District road improvement project (DRIP) reshape of feeder roads | District wide |  |  |  |  |  |  |  |  |  |  | Works Dept. |  | Cent. Admin |
| Infrastructure delivery and Management | Infrastructure Development | - Reshape of Feeder roads | Dist wide |  |  |  |  | 450,000.00 |  |  |  |  |  | Works Dept. |  | Cent. Admin |
| NATURAL RESOURCE CONSERVATION (FORESTRY) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Natural Resource Conservation | Forest Management | - Boundary Maintenance of four (4) Forest Reserves | Dist. wide |  |  |  |  |  |  | 3,500 |  |  |  | Works Dept |  | Cent. Admin |
| Natural Resource Conservation | Forest Manageanagement | - Carry out fire education through public awareness campaigns | Dist, wide |  |  |  |  |  |  | 3,500 |  |  |  | Works Dept |  | Cent. Admin |
| Natural Resource Conservation | Forest Management | - Patrols on Off-Reserve areas | Dist. wide |  |  |  |  |  |  | 3,500 |  |  |  | Works Dept |  | Cent. Admin |
| Natural Resource Conservation | Forest Management | - Monitor and supervise operations of timber harvesting | Dist. wide |  |  |  |  |  |  | 3,500 |  |  |  | Works Dept |  | Cent. Admin |
| Natural Resource Conservation | Forest Management | - Construction of fire belts | Dist. wide |  |  |  |  |  |  | 3,500 |  |  |  | Works Dept |  | Cent. Admin |
| Natural Resource Conservation | Forest Management | - Maintenance of existing plantations | Dist. wide |  |  |  |  |  |  | 3,500 |  |  |  | Works Dept |  | Cent. Admin |
| Natural Resource Conservation | Forest Management | - Tree for life project | Dist. wide |  |  |  |  | 44,207.35 |  |  |  |  |  | Works Dept |  | Cent. Admin |
| GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY (GENERAL ADMINISTRATION) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | - Tele-communication charges | AMDA |  |  |  |  | 10,000.00 |  |  |  |  |  | Works Dept. |  | Cent. Admin. |
| Management and Administration | General Administration | - Procure Office equipment, furniture and electrical accessories | AMDA |  |  |  |  | 90,000 (DACF) |  |  |  |  |  | Cent. Admin. |  | Cent. Admin |
| Management and Administration | General Administration | - Procure printed materials and stationaries | AMDA |  |  |  |  | 50,000 (DACF) |  |  |  |  |  | Cent. Admin. |  | Cent. Admin |
| Management and Administration | Human Resource Management | - Organise Capacity Building Training for Staff and Assembly members | AMDA |  |  |  |  | 40,000 (DACF) |  | 30,000 (DACF-RGF) |  |  |  | HR |  | Cent. Admin. |
| Administration | Resource Management | - Fuel and Lubricants | AMDA |  |  |  |  | 30,000 | 10,000 |  |  |  |  | Transport |  | Admin |
| Administration | Resource Management | - Community initiated project and support for MP | AMDA |  |  |  |  | 230,000.00 |  |  |  |  |  | works |  | Admin |
| Administration | Resource Management | - Maintenance and insurance of Assembly vehicles and other equipment | AMDA |  |  |  |  | 130,000.00 |  |  |  |  |  | Transport |  | Admin |
| Administration | Resource Management | - Support for the operationalisation of Area Councils | AMDA |  |  |  |  | 392,117.10 |  |  |  |  |  | Works |  | Admin |
| Administration | Resource Management | - Service National functions | AMDA |  |  |  |  | 140,000 |  |  |  |  |  | Admin |  | Admin |
| Administration | Resource Management | - Emergency prepare redness | AMDA |  |  |  |  | 50,000.00 |  |  |  |  |  | Admin |  | Finance |
| Administration | Resource Management | - Travel and Transport Allowance | AMDA |  |  |  |  | 100,000 |  |  |  |  |  | Admin |  | Finance |
| Administration | Resource Management | - Provide support to decentralised departments | AMDA |  |  |  |  | 30,000.00 |  |  |  |  |  | Cent. Admin |  | Finance |
| Administration | Resource Management | - Support to Security operations and DISEC Meetings | AMDA |  |  |  |  | 15,000.00 |  |  |  |  |  | Cent. Admin |  | Finance |
| Administration | Resource management | - Support to NALAG and Subscription | AMDA |  |  |  |  | 68.406.00 |  |  |  |  |  | Cent. Admin |  | Finance |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | DISASTER MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Disaster Prevention and Management | NADMO | - Monitoring of Schools to check crowdedness in the classrooms | All schools |  |  |  |  |  | 5,000.00 |  |  |  |  | NADMO |  | NADMO SECRETARIAT |
| Disaster Prevention and Management | NADMO | - Educate the community people on safety precaution (fire) before ,during and after using | All zones |  |  |  |  | ) |  | 5,000.00(REDD+) |  |  |  | NADMO, GNFS |  | GHANA NATIOAL FIRE SERVICE |
| . Disaster Prevention and Management | Disaster Prevention and Management | - To build the capacity of staffs in new ways of report writing on disaster assessment reports | All zones and secretariat staffs |  |  |  |  |  | 4,000 IGF |  |  |  |  | NADMO |  | DISTRICT AND REGIONAL SECRETARIAT |
| Disaster Prevention and Management | Disaster Prevention and Management | - To educate the communities on the dangers in flood when it occurs . | All flood prone areas |  |  |  |  |  | 4,000 IGF |  |  |  |  | NADMO |  | Cent. Admin |
| Disaster Prevention and Management | Disaster Prevention and Management | - Support disaster related activities and interventions and procure disaster relief items for victims | Dist. wide |  |  |  |  | 100,000.00 |  |  |  |  |  | NADMO |  | Cent. Admin |
| Disaster Prevention and Management | Disaster Prevention and Management | - Sensitization on the need for reclamation of lost lands in various zones | Selected zones in the district |  |  |  |  | 30,000.00 |  | 10,000.00 (REDD+) |  |  |  | NADMO |  | MINISTRY OF AGRIC AND FORRESTRY COMMISSION |
| Disaster Prevention and Management | NADMO | - Reduce road accident on our roads by training driver unions road safety measures | All driver unions and pragyia operators |  |  |  |  | 10,000.00 |  |  |  |  |  | NADMO |  | ARMBULANCE SERVICE , GHANA POLICE SERVICE , NCCE, GPRTU, PRAGIA UNIONS |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | - Support to DCE Engagement with the Communities | Dist. wide |  |  |  |  | 50,000 (DACF) |  |  |  |  |  | Cent. Admin. |  | Cent. Admin |
| Management and Administration | Planning, Budgeting and Coordination | - Support to District Wide Project Monitoring and Evaluation | Dist. wide |  |  |  |  | 40,000.00 (DACF) | 10,000 (IGF) |  |  |  |  | Cent. Admin. |  | Cent. Admin |
| Management and+ Administration | General Administration | - Organisation of Area Council Meetings | All 12 area Councils |  |  |  |  |  | 9,000 (IGF) |  |  |  |  | Cent. Admin. |  | Cent. Admin |
| Management and Administration | General Administration | - General Assembly and sub-committee meetings | AMDA |  |  |  |  | 93,553.30 DACF |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Gazette fee-fixing and Assembly by-laws and others | AMDA |  |  |  |  | 40,000 (DACF) |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Organize DPCU and budget committee | AMDA |  |  |  |  | 30,000 (DACF) |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Support to Annual Action Plan and Composite budget preparation | AMDA |  |  |  |  | 80,000.00 |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Support to Annual Progress Report and Budget performance reporting | AMDA |  |  |  |  | 15,000.00 ) |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Organize Social Accountability and town hall meetings | AMDA |  |  |  |  | 30,000 (DACF) |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Submission of Audit committee reports, internal audit report and audit committee meetings | AMDA |  |  |  |  | 80,000.00 |  |  |  |  |  | Internal Audit |  | Cent. Administration |
| Management and Administration | General Administration | - Organise ISSC and Management Meetings |  |  |  |  |  | 20,000.00 |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Stakeholders forum on fee fixing resolution |  |  |  |  |  | 20,000 (DACF |  |  |  |  |  | Cent. Admin |  | Cent. Admin |
| Management and Administration | General Administration | - Support for the preparation of DMTDP and special development framework | AMDA |  |  |  |  | 100,000.00 | 20,000 (IGF) |  |  |  |  | Cent. Admin |  | Cent. Admin |

Source: AMDA- DPCU, September 2025

SAMUEL KWAAH GYAN                                                                                                    HON. IBRAHIM ISSAHAK

DIST. COORDINATING DIRECTOR                                                                                 DIST. CHIEF EXECUTIVE

………………………………….                                                                                                  .……………………………..

HON. JUSTICE NKRUMAH

PRESIDING MEMBER

…………………………………